## 2025_Winter
2025-08-23 | Arrive at Preveza (i.e.Day before work starts)
2025-08-29 | Lift out date (Target for all pre-lift jobs) |  |  |  |  | Hours | %
2025-09-07 | Leave for airport (target + 1 for all jobs) |  | Outstanding |  |  | 0 | 0%
|  |  | Completed |  |  | 119.9667 | 100%
|  |  | Total Hours |  |  | 119.9667
|  |  | Hours (Tasks listed) |  |  | 119.9667 | 100%
Category | Item | Date | Location | Day | Order | Duration (mins.) | Done | Notes
Travel | Sail to Preveza | 2025-08-23 | Sailing | 0 | 1 | 0 | OK
Heads | Flush holding tank with caustic soda & fresh water | 2025-08-23 | At Anchor | 0 | 1 | 60 | OK | Half filled at Ligia in evening, extra 20l added via bowl in morning. Emptied outside Preveza
Engine | Add fuel biocide to diesel | 2025-08-23 | At Anchor | 0 | 2 | 30 | OK | Last 6 ltrs added with approx. 15mls. Marine16 (triple dose) ~ 72 litres now in tank gauge (Prob. really 30 ltrs.). 7.5mls to each 26l can
Engine | Grease filler cap seal | 2025-08-23 | At Anchor | 0 | 3 | 10 | OK
Deck | Remove & pack main sail | 2025-08-24 | At Anchor | 1 | 1 | 120 | OK
Electrical | Disconnect AM/FM radio & powered antenna | 2025-08-24 | At Anchor | 1 | 2 | 10 | OK | Antenna power light goes off when plug removed from radio
Electrical | Disconnect NavTex power connection | 2025-08-24 | At Anchor | 1 | 3 | 5 | OK | Powered via aux. switch, removed jack plug from unit
Deck | Remove & pack genoa | 2025-08-25 | At Anchor | 2 | 1 | 120 | OK | Small 1 inch tear in white material at very top of sail. Next to bolt rope, only a few inches from top.
Heads | Flush holding tank & aft. head with HCl & sea water | 2025-08-25 | At anchor | 2 | 2 | 120 | OK | Approx. 200ml 9% HCL pumped through 2 strokes over 2 hours then flushed into tank. Hose 1.2m up & 0.25 flat into tank
Heads | Clean & flush fwd. head & pipes with HCl then rinse | 2025-08-25 | At anchor | 2 | 3 | 60 | OK | Approx. 200mls added, 6 strokes x 4 over 3 hours. Pipe length approx. 3.1m
Deck | Replace all running rigging with messengers | 2025-08-25 | At anchor | 2 | 4 | 180 | OK | Outhaul knotted at clew. All done on 25th apart from traveller adjustment
Deck | Clean, lubricate & seal genoa furling top swivel | 2025-08-25 | At anchor | 2 | 5 | 60 | OK | Only cleaned outer surface of seal and smeared grease on surface to seal gap. Wrapped with cling film, duct tape and self-amalgamating tape at top. Foil slots sealed with grease.
Water System | Empty aft water tank, clean interior & vinegar rinse | 2025-08-25 | At Anchor | 2 | 6 | 60 | OK | A few black flecks & some fine sandy sediment
Engine | Change oil & renew oil filter (Yanmar 129150-35170) | 2025-08-26 | At Anchor | 3 | 1 | 150 | OK | Oil around 80% or slightly higher, removed 4l. Added 3.4l from opened can + 450ml from new one, leaves ~3.55l for 2026 level was 75% (should be ~5l) Buy more filters in Greece. Ones in Vlycho about 8.50, check Ionian
Engine | Check raw water pump seals for shaft leaks | 2025-08-26 | At anchor | 3 | 2 | 5 | OK | No sign of leakage.
Engine | Check coolant level & top up if needed | 2025-08-26 | At anchor | 3 | 3 | 5 | OK | At min., very slight drop from start of season.
Engine | Check gearbox oil (Dipstick broke at thread: Replace) | 2025-08-26 | Ashore | 3 | 4 | 60 | OK | Filled ashore and level fractionally below mark on dipstick (measured when unscrewed). 30mls added to avoid overfilling (reported to cause slipping). Total added now 480mls when oil changed
Engine | Clean anti-syphon valve | 2025-08-26 | At anchor | 3 | 5 | 15 | OK | Perfect condition as usual
Engine | Clean engine bay | 2025-08-26 | Ashore | 3 | 6 | 15 | OK | Small amount of oil from oil change, easily cleaned
Deck | Remove wind generator. Remove tail fin & store | 2025-08-27 | At Anchor | 4 | 1 | 90 | OK | Front cover needs to be fixed (60mins. To remove from pole.)
Ancilliaries | Service Honda Generator (oil change, air filter, drain fuel) | 2025-08-27 | At anchor | 4 | 2 | 180 | OK | Only 12 hours use, oil not changed (400mls), fogging oil. Still to do : Clean & oil air filter (Not really needed yet)
Electrical | Check Deck level nav. lights | 2025-08-27 | At Anchor | 4 | 3 | 120 | OK | All working, incl. steaming & anchor. Contralube added again to all deck level lights. No corrosion, cracks etc. found
Ancilliaries | Padlock Generator in locker | 2025-08-27 | Ashore | 4 | 4 | 5 | OK
Water System | Clean tap and shower filters | 2025-08-28 | At anchor | 5 | 1 | 15 | OK | Minimal grit in tap filter
Engine | Check water separator | 2025-08-28 | At anchor | 5 | 2 | 10 | OK | Clear, no water or sediment
Ancilliaries | Add fuel stabiliser to petrol | 2025-08-28 | At anchor | 5 | 3 | 5 | OK | Added 30mls stabiliser to 2.5ltrs petrol
Electrical | Top up batteries | 2025-08-28 | At anchor | 5 | 4 | 30 | OK | Batteries only 98% check SG in yard when charged
Water System | Empty 20l water containers and add vinegar | 2025-08-28 | At anchor | 5 | 5 | 60 | OK
Heads | Final flush through holding tank with fresh water | 2025-08-29 | At anchor | 6 | 1 | 10 | OK | Fill & empty en-route from Hospital bay (Forgot to outlet close valve when flushing)
Heads | Flush through holding tank with washing up liquid & drain | 2025-08-29 | At anchor | 6 | 2 | 30 | OK | Drain en-route to lift out
Heads | Clean & flush heads & pipes with fresh water then drain | 2025-08-29 | At anchor | 6 | 3 | 120 | OK | En route to lift out
Hull | Clean hull below waterline incl prop.shaft & rudder etc. | 2025-08-29 | Ashore | 6 | 4 | 150 | OK | Light pressure wash. Only a few barnacles to remove at bow, skeg, rudder and above rudder
Hull | Bow thruster - remove props & clean | 2025-08-29 | Ashore | 6 | 5 | 80 | OK | Look pretty clean after 3 months. A few barnacles
Hull | Check anodes (size, wear etc.) | 2025-08-29 | Ashore | 6 | 6 | 10 | OK | One shaft & prop anode to replace. Hull anode to change next year. Check required rod & nut size.
Hull | Check rudder bearings | 2025-08-29 | Ashore | 6 | 7 | 10 | OK | Negligibl play found.
Hull | Remove log & service and put in blanking plug | 2025-08-30 | At anchor | 7 | 1 | 20 | OK | Pretty clean with one small barnacle. Needs final clean before antifouling
Ancilliaries | Remove dinghy chaps & wash & dry (Keep dinghy covered afterwards) | 2025-08-30 | Ashore | 7 | 2 | 120 | OK | Looking pretty clean, some sewing required at rear of vinyl section
Ancilliaries | Wash dinghy, check & note repairs | 2025-08-30 | Ashore | 7 | 3 | 120 | OK | Looking very clean. Re-glue one D-ring point holding chaps in place
Water System | Empty 5l water containers and add vinegar | 2025-08-30 | Ashore | 7 | 4 | 60 | OK | Started en-route as they were being emptied, last one on 18th
Deck | Wash running rigging | 2025-08-30 | Ashore | 7 | 5 | 150 | OK | Mostly completed on 7th, spinnaker & genoa on 8th, traveller on 19th
Hull | Check cutless bearing (Clean prop & shaft properly) | 2025-08-31 | Ashore | 8 | 1 | 60 | OK | No sign of any wear at all in cutless bearing.
Hull | Wash | 2025-08-31 | Ashore | 8 | 2 | 360 | OK
Deck | Wash topsides & deck | 2025-08-31 | Ashore | 8 | 3 | 360 | OK
Hull | Apply oxalic acid | 2025-08-31 | Ashore | 8 | 4 | 120 | OK
Deck | Apply oxalic acid on topsides & stainless steel | 2025-08-31 | Ashore | 8 | 5 | 120 | OK
Hull | Polish | 2025-09-01 | Ashore | 9 | 1 | 150 | OK
Deck | Polish topsides & deck | 2025-09-01 | Ashore | 9 | 2 | 120 | OK
Engine | Run acetic acid/citric acid through heat exchanger | 2025-09-01 | Ashore | 9 | 3 | 60 | OK | Short fresh water flush, add 2.5l 6% acetic & 340ml lemon juice to water filter. Run to displace to heat exchanger leave 12hours
Electrical | Remove solar regulator (Marlec HRDi) fuse | 2025-09-01 | Ashore | 9 | 4 | 30 | OK | 40A fuses removed from each side (Dom. & Engine switches) N.B. 30A Epever output fuse corroded, replaced & Contralube used.
Electrical | Remove deck solar panels (65W + 2x40W) | 2025-09-01 | Ashore | 9 | 5 | 45 | OK | Disconnected & stored (Fwd. cabin & aft port locker)
Deck | Service windlass and examine top seal | 2025-09-01 | Ashore | 9 | 6 | 0 | Skip | Usually 60 mins. Serviced & top seal in good condition last year. Due to check brushes in 2026
Deck | Seal boom ends with cling film & duct tape | 2025-09-01 | Ashore | 9 | 7 | 30 | OK
Electrical | Pack plotter, VHF, EPIRB, radios & radio | 2025-09-01 | Ashore | 9 | 8 | 0 | Skip | Was 60 mins.
Deck | Check mainsheet traveller bearings for wear & clean | 2025-09-01 | Ashore | 9 | 9 | 30 | OK | Sprayed with PTFE lube. Rinse with fresh water and use more PTFE in spring 2026
Deck | Clean stainless steel with Autosol | 2025-09-01 | Ashore | 9 | 10 | 180 | OK
Electrical | Turn off boost on mains charger (1,3 on 2,4,5 off in summer) | 2025-09-01 | Ashore | 9 | 11 | 30 | OK | Switch 1 off, Switch 3 on. No boost, 13.5V float
Interior | Remove cushion covers | 2025-09-01 | Ashore | 9 | 12 | 0 | Skip | Was 15 mins.
Water System | Clean water filter | 2025-09-01 | Ashore | 9 | 13 | 0 | Skip | O-ring swollen, leave unopened. Looks clean from outside (Was 20 mins.)
Interior | Fit winter curtains | 2025-09-01 | Ashore | 9 | 14 | 60 | OK | Only deck ones in front of mast left, done in evening on 6th
Deck | Wash cockpit & partial polish | 2025-09-01 | Ashore | 9 | 15 | 60 | OK
Deck | Fit winch covers | 2025-09-01 | Ashore | 9 | 16 | 20 | OK
Deck | Fit wheel covers | 2025-09-01 | Ashore | 9 | 17 | 5 | OK
Electrical | Remove one solar panel and configure MPPT regulator | 2025-09-02 | Ashore | 10 | 1 | 90 | OK | Expected min. daily output (Dec.) per 100W 0.115kWh or ~8Ah per day
Engine | Check oil level | 2025-09-02 | Ashore | 10 | 2 | 5 | OK | Very slighty below max. now boat is ashore, slightly bow raised.
Engine | Flush raw water system with fresh water & antifreeze | 2025-09-02 | Ashore | 10 | 3 | 60 | OK
Engine | Remove fan belt | 2025-09-02 | Ashore | 10 | 4 | 30 | OK | Removed fresh water pump pulley to check behind. No coolant leak seen, tissues placed to spot any leak over winter.
Engine | Remove raw water impeller | 2025-09-02 | Ashore | 10 | 5 | 15 | OK | Remove expansion cap with hose (Stops contents syphoning out over winter in event of any seepage when system gets very cold)
Engine | Spray engine with rust inhibitor | 2025-09-02 | Ashore | 10 | 6 | 10 | OK | Used WD 40 & fogging oil
Engine | Drain water trap via seacock | 2025-09-02 | Ashore | 10 | 7 | 5 | OK
Engine | Check & clean strainer | 2025-09-02 | Ashore | 10 | 8 | 3 | OK
Engine | Remove water injection elbow, clean & replace | 2025-09-02 | Ashore | 10 | 9 | 45 | OK | Slight oily carbon build up. Cleaned & looks OK, Faces & gasket (now in 2 parts) cleaned. Light smear of 2-4-C grease on all faces
Engine | Spray heat exchanger element core with rust inhibitor | 2025-09-02 | Ashore | 10 | 10 | 15 | OK | Used fogging oil into exchanger, exhaust & intake manifolds
Deck | Polish stainless steel | 2025-09-02 | Ashore | 10 | 11 | 60 | OK | Winter polish
Ancilliaries | Winterise Outboard (water flush, fuel stabiliser, fogging & gear box oil) | 2025-09-02 | Ashore | 10 | 12 | 180 | OK | All ready for next season with 90mls oil added to bottom hole using syringe - engine on its side with prop. end raised (Lost some, prob. 80-85 mls). Leaked last year, check fenderbase for oil in 2025
Deck | Wash fenders and lifebuoy | 2025-09-02 | Ashore | 10 | 13 | 180 | OK
Deck | Wash anchor & chain & check markings | 2025-09-03 | Ashore | 11 | 1 | 120 | OK | Chain laid out on pallet. A couple of markings to redo in 2026
Deck | Remove windlass winch handle | 2025-09-03 | Ashore | 11 | 2 | 5 | OK
Deck | Remove windlass remote & seal wires | 2025-09-03 | Ashore | 11 | 3 | 20 | OK
Deck | Wash anchor chain locker | 2025-09-03 | Ashore | 11 | 4 | 60 | OK | Some mud & weed. Oxalic for some rust stains
Deck | Fill anchor locker, bag cans & use wasp spray & soap | 2025-09-03 | Ashore | 11 | 5 | 60 | OK
Interior | Bilges - empty & clean | 2025-09-03 | Ashore | 11 | 7 | 120 | OK
Deck | Wash batty line sun shields | 2025-09-03 | Ashore | 11 | 8 | 0 | Skip | Not cleaned, hardly used since last clean (usually 30 mins. job)
Interior | Fwd & aft. heads cleaned (Remove plugs & drain pipes) | 2025-09-03 | Ashore | 11 | 9 | 60 | OK | Dismantle pumps in 2026 and replace valves etc.
Electrical | Spray speaker & switches with rust inhibitor | 2025-09-03 | Ashore | 11 | 10 | 10 | OK | Only sprayed speaker with Fogging oil, covers on switches still intact (not sprayed)
Electrical | Seal plotter wires | 2025-09-03 | Ashore | 11 | 11 | 10 | OK
Hull | Burnish prop. and p-bracket. coat with equ-mate | 2025-09-03 | Ashore | 11 | 12 | 10 | OK
Interior | Wash window netting | 2025-09-03 | Ashore | 11 | 13 | 0 | Skip | Was 120 mins. Large ones done already in Itea, leaves 3 small ones for 2026
Electrical | Move bowthruster battery & connect to engine battery | 2025-09-04 | Ashore | 12 | 1 | 60 | OK | Remove 10A fuse & replace after engine winterised. Wires stored in engine battery compartment - aft cabin
Electrical | Clean battery compartment fan | 2025-09-04 | Ashore | 12 | 2 | 30 | OK | Not too much fluff
Electrical | Check electrolyte levels on batteries & log SG | 2025-09-04 | Ashore | 12 | 3 | 60 | OK | SG all OK All cells overfilled by 20mls for winter (25mls &30mls for 2 initially sl. low)
Electrical | Disconnect smartguage | 2025-09-04 | Ashore | 12 | 4 | 15 | OK | Was reading 100% for 2-3 days before disconnecting
Electrical | Disconnect Bluetooth Amp./Volt/Watt meter | 2025-09-04 | Ashore | 12 | 5 | 5 | OK | Switch turned off, display blank
Hull | Close Seacocks (Also move to exercise & record any stiffness) | 2025-09-04 | Ashore | 12 | 6 | 10 | OK | All closed except galley. Fwd head stiff as usual no other problems noted. Replaced engine intake in 2023 All taps left slightly open to prevent then sticking closed.
Hull | Plug all skin fittings, drains (transom) & exhaust | 2025-09-04 | Ashore | 12 | 7 | 60 | OK | All plugged except galley
Deck | Bag remaining rigging lines | 2025-09-04 | Ashore | 12 | 8 | 10 | OK | Winch switch cover also fitted
Interior | Bilges - spray rust inhibitor or put fogging oil on keel bolts | 2025-09-04 | Ashore | 12 | 9 | 10 | OK
Electrical | Charge radios Cobra VHF handheld & Midland radios | 2025-09-04 | Ashore | 12 | 11 | 10 | OK | Cobra charged, Midland are now AA and use external charger
Deck | Fit instrument & binnacle covers | 2025-09-04 | Ashore | 12 | 12 | 30 | OK
Deck | Plug all external holes incl. stern, vents, etc. | 2025-09-04 | Ashore | 12 | 13 | 20 | OK | Some bubble wrap in stern & foam in vents for water, diesel and gas
Water System | Empty forward water tank, vinegar rinse & clean interior | 2025-09-05 | Ashore | 13 | 1 | 100 | OK
Water System | Drain water system (including stern shower) | 2025-09-05 | Ashore | 13 | 2 | 20 | OK | Try feeding bleach into hot water system next year
Water System | Drain hot water tank (final vinegar rinse) | 2025-09-05 | Ashore | 13 | 3 | 60 | OK | Fed in some bleach first. Looks clean but did get black flecks. Most removed, needs further clean. Added 100mls vinegar All assembled. Lost screw from immerser cap & nut into bilge
Water System | Remove & clean hot water element | 2025-09-05 | Ashore | 13 | 4 | 60 | OK | Almost no calcification, cleaned with HCl
Deck | Fit hatch covers | 2025-09-05 | Ashore | 13 | 5 | 30 | OK | All fitted except washboard
Water System | Dismantle main pump | 2025-09-05 | Ashore | 13 | 6 | 0 | Skip | Allow 60 mins. Diaphram kit: 09-46779-01 Pump head kit: 09-46782-03
Ancilliaries | Final clean, dry, pack loosely & store dinghy | 2025-09-05 | Ashore | 13 | 7 | 120 | OK
Deck | Fit side skirts and add cable ties | 2025-09-05 | Ashore | 13 | 8 | 60 | OK | Cable ties added to lock all knots. Extra ties on all points to backup the string ties
Deck | Polish cockpit | 2025-09-06 | Ashore | 14 | 1 | 30 | OK
Ancilliaries | Winterise bikes & store | 2025-09-06 | Ashore | 14 | 1 | 90 | OK
Deck | Fit table cover | 2025-09-06 | Ashore | 14 | 2 | 5 | OK | Larger poly bag to cover table with fitted cover on top
Deck | Remove awning | 2025-09-06 | Ashore | 14 | 3 | 20 | OK | Undid middle 1st then stern & pulled webbing through. Worked well
Deck | Remove sprayhood | 2025-09-06 | Ashore | 14 | 4 | 20 | OK | Pictures taken of area needing repair
Deck | Examine sprayhood & Awning | 2025-09-06 | Ashore | 14 | 5 | 30 | OK | Sprayhood still leaks near middle, slightly to stbd. Awning needs proofing on last 6" of front and all of back section, also small hole to patch
Interior | Forecabin storage | 2025-09-06 | Ashore | 14 | 6 | 120 | OK
Interior | Storage & packing | 2025-09-06 | Ashore | 14 | 7 | 360 | OK | Still to move stbd back cushions
Interior | Check for any minor leak on galley window | 2025-09-06 | Ashore | 14 | 8 | 10 | OK | Full pressure spray on all windows except rear. One drip on galley, seal wiped and repeated. All OK, no sign of any water.
Interior | Remove cooker & clean recess | 2025-09-06 | Ashore | 14 | 9 | 60 | Skip | Recenly cleaned
Interior | Remove cooker battery | 2025-09-06 | Ashore | 14 | 10 | 5 | OK | Remove clocks, weather station and TV remote as well
Interior | Pack TV | 2025-09-06 | Ashore | 14 | 12 | 5 | OK | Remote in fwd cabin wardrobe, RHS
Deck | Disconnect gas bottle | 2025-09-06 | Ashore | 14 | 13 | 15 | OK | Disconnected after evening meal, some silicone grease on cap to seal. 50% left 0.75kg (5.4-3.5kg) & 10% left (3.7-3.4kg)
Interior | Shut all curtains | 2025-09-06 | Ashore | 14 | 14 | 10 | OK | Early start so no need to open in morning
Travel | 06:30 breakfast & final packing & checks for 2 hours | 2025-09-07 | Ashore | 15 | 1 | 120 | OK
Interior | Fill dessicant containers | 2025-09-07 | Ashore | 15 | 3 | 10 | OK
Hull | Close galley seacock & block skin fitting | 2025-09-07 | Ashore | 15 | 4 | 10 | OK | Tap left slightly open to reduce chance of it siezing closed
Electrical | Turn off all battery switches | 2025-09-07 | Ashore | 15 | 6 | 5 | OK
Electrical | Disconnect mains power & take picture of meter | 2025-09-07 | Ashore | 15 | 7 | 5 | OK
Deck | Tie on main hatch cover | 2025-09-07 | Ashore | 15 | 8 | 5 | OK | Lock knots with cable ties
Travel | 10:00 leave for airport (Christophe) | 2025-09-07 | Ashore | 15 | 9 | 0
Travel | 10:15 arrive at airport (Gate closes 10:55) | 2025-09-07 | Ashore | 15 | 10 | 0
Travel | 11:25 flight EZY8248 expected takeoff time | 2025-09-07 | Ashore | 15 | 11 | 0
Formulas:
Date = A1+[Day]
Note on B21: Author: Ionion sell Tokio FL-304 (W811/80?) if Yanmar part not available.
Note on I63: Author: Summer position was 1,3 on & 2,4,5 off 1 Boost on 3 Batt. Type 3 (Lead acid, Ca) 14.1/13.4V but adjusted with pot.
Note on I70: Author: https://re.jrc.ec.europa.eu/pvg_tools/en/tools.html Use performance off-grid & make usage higher than panel output to show max. output

## 2026_Spring
| Item | Date | Notes
Ancilliaries | Check outboard
| Replace lifejacket lights | N/A
| Replace lifejacket triggers | N/A
| Service lifejackets | N/A
| Service jonbuoy | N/A
Batteries | Check electrolyte level | 2026-04-11
| Check & clean all battery terminals | N/A | All look clean, left as not launching
| Replace fuse in solar regulator | 2026-04-13 | Fitted before deck solar panels
| Refit bowthruster battery | N/A | No launch planned for 2026
Bow Thruster | Antifoul | 2026-05-21
| Lubricate shaft with silicone grease | 2026-05-21
| Refit blades | 2026-05-21 | N.B. Offset blades
Cockpit | Apply biocide to teak sole & seats | N/A | Not really required very often in Greece
| Apply Deks Olje to flagstaff | N/A | Not launching, so left in storage
| Clean & lubricate winches | N/A | Carried out late last year, no planned use 2026
| Clean & lubricate mainsheet track | 2026-05-19 | Usual wash and then PTFE dry lubricant
| Clean gas bottle cocker | 2026-05-22
| Clean port locker | 2026-05-21
| Clean starboard locker | 2026-05-21
| Clean stern locker | 2026-05-21
| Polish fibreglass | N/A | Minor clean, no launch planned
| Polish stainless steel | 2026-04-13
| Refit awning | 2026-04-16
| Refit liferaft (check upright strut) | N/A | Cannister stored in place over last winter
| Refit sprayhood | 2026-04-16
| Refit wind generator | N/A | No launch planned for 2026
| Wash fibreglass | 2026-05-09
| Wash teak sole & seats | 2026-05-10
Deck | Apply biocide to teak deck | N/A | Not really required very often in Greece
| Check brushes on windlass | N/A
| Clean safety lines | 25/5/
| Polish fibreglass | N/A | No launch planned in2026, winter polish left on
| Polish stainless steel | N/A
| Refit solar panels | 2026-04-13
| Refit windlass remote | 2026-05-18 | Contralube used then sealed as usual
| Wash fibreglass | N/A
| Wash teak decks | 2026-05-09
Engine | Check cable straps | 2026-05-07
| Check coolant level | 2026-05-07
| Check exhaust elbow | N/A | Checked end 2025 & still perfect.
| Check fuel sump for contamination and add biocide | N/A | Clean end 25, 100 litres+double Marine 16, 26
| Check gear box oil | 2026-05-07
| Check hose clamps | 2026-05-07
| Check mounts | 2026-05-07
| Check oil level | 2026-05-07
| Drain water from fuel separator | N/A | Clean end 25
| Grease shaft seal |  | Usual method, 1ml correct grease via straw
| Renew fuel filter | N/A | Filter available, change post launch as usual
Replace fan belt
Replace impeller (pump rotates clockwise)
| Spray electrical connections with WD40 | 2026-05-07
Heads | Check for leaks at top pump seal
Flush through with fresh water
| Clean aft. heads | 2026-05-01
| Clean forward heads | 2026-05-01
Service valves and O-rings
Hull | Antifoul | 2026-05-25
| Apply udder ointment to waterline | N/A | Pre-launch job
| Check hull anode | 2026-05-23 | New anode fitted, continuity good to P-bracket
Polish
Wash
Interior | Clean & condition cushions |  | Clean 1:35 hrs Condition 1 hr (3hrs)
| Clean aft cabin | 2026-04-23
| Clean fore cabin | 2026-05-01
| Clean saloon | 2026-05-01
| Clean windows | 2026-05-12
| Replace summer curtains | 2026-05-12
| Replace summer cushion covers | N/A | Not removed
| Vacuum and wash bilges | 2026-05-25
| Wash and clean all surfaces | 2026-05-12
Log | Antifoul | 2026-05-25 | Cleaned, checked and painted
| Apply udder ointment | N/A
| Refit | 2026-05-27 | New o-rings fitted
Mast & Rigging | Exercise & lubricate bottle screws
Grease mainsail furling gear
Hoist genoa
Hoist mainsail
Inspect & lubricate sheaves if necessary
Inspect all rigging & deck fittings
Inspect standing rigging for wear
| Refit running rigging | 2026-05-17 | Messengers washed & stored for layup
| Refit wind sensor | N/A | Not removed
Re-tune Standing rigging
Service forestay top swivel
Tape all split pins
Propeller | Burnish | 2026-05-23
| Cover propellor & p-bracket with udder ointment | N/A
| Inspect prop shaft and nut | 2026-05-09
| Inspect cutless bearing | 2026-05-09
| Replace propeller anode | 2026-05-23 | Small amount of Contralube, end hole sealed
| Replace shaft anode | 2026-05-19 | Seems better quality anode this year
Seacocks | Carry out continuity test between engine & seacock
Lubricate with PTFE
Steering | Inspect and lubricate steering sheaves | 2026-05-22 | No sign of wear or Cable damage
| Inspect cable tension | 2026-05-22 | No change in tension, all good
Water Syatem | Clean out water system pump strainer | 2026-05-10
| Flush through with fresh water | 2026-04-14 | Aft. only as fwd. tank still in layup mode
| Inspect for leaks | 2026-05-14
| Hot watertank - heat , vinegar soak overnight | 2026-04-14
| Hot watertank - drain & flush | 2026-04-15

## ItemsSkipped
Ancilliaries | Remove & clean jackstays | Not used in 2025
Ancilliaries | Wash solar showers with bleach | Not used in 2025
Ancilliaries | Service lifejackets and MOB device | Short of time, leave until 2026
Ancilliaries | Check brushes on Caframo fan | Doesn't seem to be easy to dismantle, may not be possible
Deck | Service windlass gypsy seal | Not needed as it was replaced when windlass serviced recently and not used much since.
Deck | Wash teak decks and cockpit (Fairy liq.) | Should be pretty clean after heavy rain for a few days
Deck | Check windlass gearbox oil | Already changed at last service
Deck | Apply deck biocide | N/A
Deck | Caulk teak deck in cockpit & side decks | Started but short of time to complete
Engine | Starter motor | Planned to remove & check brushes but negligible wear found when last dismantled
Hull | Quick wash & clean (remove stains) | Skipped due to poor weather earlier (Usually done from dinghy when calm)
Interior | Clean hatch screens (by removing netting) | Short of time and most were properly cleaned in Itea
Interior | Fire extinguisher - check & shake | Carried out mid-season